## Activity Log
Name: |  | Project Group Number 5
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity (hours): | Completed? | Notes: | Name:
1 | 27/04/2023 | Meeting to think of different idea, and delegate researching one topic each | 0.5 | Yes |  | Group task
1 | 27/04/23 | Research datasets (spotify, imbd, covid), APIs (google trends, omdb) | 2 | Yes | We did not end up using these | Maria
1 | 27/04/23 | Setting up Jamboard with personal interests, topic ideas, project timeline, etc | 1.5 | Yes | We did not end up using these | Maria
1 | 27/04/2023 | Researched datasets and API's using Kaggle and open source data | 2 | Yes | ended up using diferent data sets | Fussilat
1 | 28/04/2023 | Researched datasets and APIs, found Kaggle survey dataset | 3 | Yes |  | Sarah
1 | 28/4/2023 | Research topics and publically available datasets | 2 | Yes |  | Clare
2 | 02/05/2023 | Meeting with Kosi to dicuss ideas and clarify we are heading in the right direction. Delegated a year of data to each member of the group, with homework to analyse specific year's data and come up z up with question sets. | 1.5 | Yes |  | Group task
2 | 04/05/2023 | Set up google collab and discussed how we would clean data | 1 | Yes |  | Group task
2 | 05/05/2023 | Cleaning data 2022 | 8 | Yes |  | Sarah
2 | 05/05/2023 | Clean 2017 data | 5 | Yes |  | Clare
2 | 05/05/2023 | Clean 2019 data | 4 | Yes |  | Fussilat
2 | 05/05/2025 | Clean 2020 data | 4 | Yes |  | Liman
2 | 06/05/2023 | Cleaning data 2021 | 8 | Yes |  | Maria
2 | 06/05/2023 | Cleaning data 2018 | 4 | Yes |  | Dabrowka
2 | 07/05/2023 | Group meeting organise further cleaning of data and conceptualise project | 3.5 | Yes |  | Group task
3 | 08/5/2023 | Group meeting to discuss merging of the dataset | 2.5 | Yes |  | Group task
3 | 12/05/2023 | Spoke with group after class to delegate tasks and refine question set, as well as decide on data that will be used | 1 | Yes |  | Group task
3 | 14/5/2023 | Group meeting to discuss APIs and documentation | 3.5 | Yes |  | Group task
4 | 15/5/2023 | Group meeting to finalise data cleaning methods and discuss APIs and next steps | 2.5 | Yes |  | Group task
4 | 16/05/2023 | Research Ordinal Logistic Regression Model | 2 | Yes |  | Sarah
4 | 17/5/2023 | Cleaning 2017 data and add currently conversion API | 3 | Yes |  | Clare
4 | 20/05/2023 | Discusion how to join cleaned dataframes from each year, droping and renamig colums | 7 | Yes |  | Group task
4 | 20/05/2023 | Slide template | 1 | Yes |  | Maria
4 | 20/05/2023 | Research about merging datasets, create mapping to standardise the inconsistent records | 2 | Yes |  | Liman
4 | 21/05/2023 | Merging datasets meeting, begin drafting report and presentation | 8 | Yes |  | Group task
4 | 22/05/2023 | Made additions to the Presentation, and report | 1 | Yes |  | Fussilat
5 | 23/05/2023 | Setting dummy variables Working on regresion model | 3 | Yes |  | Liman
5 | 23/05/2023 | Work on inflation API Working on regresion model | 6 | Yes |  | Maria
5 | 23/05/2023 | Implement Ordinal Logistical Regression Model and appropriate tests | 4 | Yes |  | Sarah
5 | 23/05/2023 | Work on Q1 Visualisation | 4 | Yes |  | Fussilat
5 | 23/05/2023 | Continue working on Q1 visualisation | 0.5 | Yes |  | Liman
5 | 23/5/2023 | Q2 visualisation | 3.5 | Yes |  | Clare
5 | 24/05/2023 | Q1 visualisation continued | 3 | Yes |  | Fussilat
5 | 26/05.2023 | Q3 Visualising data | 7 | Yes |  | Maria
5 | 26/05.2023 | Calculate inflation changes and decide visualisations for the report | 3 | Yes |  | Liman
5 | 27/05/2023 | Visualise data and continue drafting project report | 5 | Yes |  | Group task
5 | 27/05/2023 | Create the ReadMe file | 1 | Yes |  | Liman
5 | 27/05/2023 | Download the Jupyter Notbook file from Google colab, Organize File Folders, Add comments to the code | 2 | Yes |  | Liman
5 | 27/05/23 | Visualising data (Q3) | 7 | Yes |  | Maria
5 | 28/05/2023 | Finalise visualisations and report | 12 | Yes |  | Group task
|  | Total Hours Spent | 144.5